## ETP-Open
ID | Title | Assigned To | State | Severity | Stack Rank | Priority | Created By | Created Date | Found In | Iteration Path
11598 | Dev server - ISPO- Late finish- Count mismatch in tabular data, chart, OTD trend | Anu James | Active | 2 - High |  | 2 | Reshmimol K.K. | 10/14/2021 3:10 PM | 3.3.2.7 (dev server) | ETP\IEP-3.3.2.6
11542 | TPO- Actual not correct | Bajila Salim | Active | 3 - Medium |  | 2 | Teena Varghese | 2021-08-10 23:15 |  | ETP\IEP-3.3.2.6
11744 | Quality book - Dev server - No data displayed in generated PPT | Jeetu James | New | 2 - High |  | 2 | Jeetu James | 2021-12-11 13:41 | 3.3.3.12 | ETP\IEP-3.3.3.0
11755 | Dev server _ Performance issue in contracts loading. | Juby C. Samuel | New | 3 - Medium |  | 2 | Aneesha Chandramohan | 11/15/2021 6:56 PM | 3.3.3.1 | ETP\IEP-3.3.3.0
11679 | IEP Data Validation | Nazila Ulli | New | 3 - Medium |  | 2 | Brilsa Raj | 10/29/2021 10:30 AM |  | ETP\IEP-3.3.3.0
11582 | Devserver _ SYSTEM DR1 _ PERFORMANCE ISSUE | Thanseer P.R. | New | 1 - Critical |  | 2 | Aswin Sreesh | 2021-09-10 21:41 | 3.3.2.6 | ETP\IEP-3.3.2.6
11674 | Production server - favorites spelling not correct | Thanseer P.R. | New | 3 - Medium |  | 2 | Reshmimol K.K. | 10/27/2021 5:25 PM | 3.3.3.0 | ETP\IEP-3.3.2.6
11675 | Production Server - Even the checkbox is in unselected state, the data is displaying. | Thanseer P.R. | New | 3 - Medium |  | 2 | Reshmimol K.K. | 10/27/2021 5:30 PM | 3.3.3.0 | ETP\IEP-3.3.2.6
11676 | Production server - Column Name to be corrected | Thanseer P.R. | New | 3 - Medium |  | 2 | Reshmimol K.K. | 10/27/2021 5:31 PM | 3.3.3.0 | ETP\IEP-3.3.2.6
11678 | Ispo Risk- Comments with attachment option is not done | Thanseer P.R. | New | 3 - Medium |  | 2 | Brilsa Raj | 10/28/2021 10:27 AM |  | ETP\IEP-3.3.3.0
11822 | Developer Testing-Generic DR Work Flow | Thanseer P.R. | New | 3 - Medium |  | 2 | Amala M R | 12/18/2021 12:14 AM | 3.3.3.27 | ETP\IEP-OP-2111
11677 | Post Processing Tool- | Urvasi G. | New | 3 - Medium |  | 2 | Brilsa Raj | 10/27/2021 11:25 PM |  | ETP\IEP-3.3.3.0

## ETP-Resolved
ID | Title | Severity | Priority | State | Reason | Stack Rank | Assigned To | Changed Date | Created By | Created Date | Found In | Iteration Path
11766 | global operations(data leak)_sub-P&L is not showing in export file | 3 - Medium | 2 | Resolved | Fixed |  | Mugesh V. Kannan | 2021-03-12 14:47 | Mugesh V. Kannan | 11/29/2021 8:56 PM | 3.3.3.13 | ETP\IEP-OP-2111
11768 | Observations_Global Operation_issue in data displaying | 3 - Medium | 2 | Resolved | Cannot Reproduce |  | Mugesh V. Kannan | 2021-03-12 14:46 | Mugesh V. Kannan | 11/30/2021 12:17 PM | 3.3.3.13(debug) | ETP\IEP-OP-2111
11767 | NPD_LE_Loading issue | 3 - Medium | 2 | Resolved | Fixed |  | Amala M R | 11/30/2021 1:34 PM | Amala M R | 11/29/2021 10:22 PM | 3.3.3.13 | ETP\IEP-OP-2111
11535 | For Some documents, DOC type is not avaialble in Tabular data. | 3 - Medium | 2 | Resolved | Fixed |  | Mohamed Ilyaz Sulaiman | 10/26/2021 4:12 PM | Teena Varghese | 2021-08-10 21:07 |  | ETP\IEP-3.3.2.6
11530 | "Bugs like showing and not showing current resources/wrong resources are observed. To validate more on this. Sync Issue . Switching between Auto Assigned /Wrong resource and -Second API call get First API result" | 3 - Medium | 2 | Resolved | Fixed |  | Mohamed Ilyaz Sulaiman | 10/26/2021 4:11 PM | Teena Varghese | 2021-08-10 21:00 |  | ETP\IEP-3.3.2.6
11544 | "When project status is selected as “Inactive”….why inactive projects are also in Current projects? If any open points in Inactive projects like VDR-REV , VDR-FIN or TA, can IEP highlight that sub module for attention(New used case)? " | 3 - Medium | 2 | Resolved | Fixed |  | Mohamed Ilyaz Sulaiman | 10/26/2021 4:08 PM | Teena Varghese | 2021-08-10 23:16 |  | ETP\IEP-3.3.2.6
11581 | P6 Resource- "Bugs like showing and not showing current resources/wrong resources are observed. To validate more on this. Sync Issue . Switching between Auto Assigned /Wrong resource and -Second API call get First API result" | 3 - Medium | 2 | Resolved | Fixed |  | Mohamed Ilyaz Sulaiman | 10/26/2021 4:07 PM | Teena Varghese | 2021-09-10 14:08 |  | ETP\IEP-3.3.2.6
11178 | ISPO/VDR/VDR-Rev-Weekly Forecast/UI-Individual/Descipline/Office view-Target date-Tabular data not coming | 3 - Medium | 2 | Resolved | Cannot Reproduce |  | Bajila Salim | 10/19/2021 10:13 AM | Bajila Salim | 2021-04-08 15:31 |  | ETP
11401 | IEP- Sanity test - Select all button not working for past projects | 3 - Medium | 3 | Resolved | Copied to Backlog |  | Jeetu James | 9/28/2021 12:50 PM | Jeetu James | 9/17/2021 12:47 PM | 3.3.2.5 dev | ETP\IEP-3.3.2.4
10184 | Platform Usage - Export Date issue - It contains future data as well- in BH laptop - contact sreeni | 3 - Medium | 2 | Resolved | Fixed |  | Gireesh Areekkal | 4/22/2021 12:23 PM | Gireesh Areekkal | 3/22/2021 5:13 PM |  | ETP\IEP-3.3.2.0

## ETP-Active
ID | Stack Rank | Priority | Severity | State | Title | Assigned To | Tags | Created By | Created Date | Found In | Iteration Path
11598 |  | 2 | 2 - High | Active | Dev server - ISPO- Late finish- Count mismatch in tabular data, chart, OTD trend | Anu James |  | Reshmimol K.K. | 10/14/2021 3:10 PM | 3.3.2.7 (dev server) | ETP\IEP-3.3.2.6
11542 |  | 2 | 3 - Medium | Active | TPO- Actual not correct | Bajila Salim |  | Teena Varghese | 2021-08-10 23:15 |  | ETP\IEP-3.3.2.6

## ETP-Deffered
ID | Stack Rank | Priority | Severity | State | Title | Assigned To | Changed Date | Created By | Created Date | Found In | Iteration Path
11756 |  | 2 | 3 - Medium | Resolved | Dev Server & ITT Server 30% & 90% Guildeline Picture column not present in excel export file | Shreedevi I. Manjari | 2/21/2022 1:20 PM | Shreedevi I. Manjari | 11/15/2021 7:40 PM | 3.3.3.1 | ETP\IEP-3.3.3.0
11737 |  | 2 | 3 - Medium | Resolved | ITT_ EMST 60% _ Alignment issue. | Aneesha Chandramohan | 2/21/2022 1:19 PM | Aneesha Chandramohan | 2021-11-11 12:13 | 3.3.3.11 | ETP\IEP-3.3.3.0
11699 |  | 2 | 3 - Medium | Resolved | ITT_ EMST 60%_ Guideline picture is missing in the excel export and reviewer's checklist. | Aneesha Chandramohan | 2/21/2022 1:18 PM | Aneesha Chandramohan | 2021-08-11 15:18 | 3.3.3.1 | ETP\IEP-3.3.3.0
11795 |  | 2 | 2 - High | Resolved | Production Issue - IEP-Offline Issue - Observations. | Reshmimol K.K. | 2/21/2022 9:59 AM | Reshmimol K.K. | 2021-07-12 10:08 | 3.3.2.3 | ETP\IEP-OP-2111
11637 |  | 2 | 3 - Medium | Resolved | Dev server _ System DR1_ Pre work completed button navigates to wrong discipline value with invalid id no. | Aswin Sreesh | 10/26/2021 12:03 PM | Aswin Sreesh | 10/20/2021 11:48 AM |  | ETP\IEP-3.3.2.6
11648 |  | 2 | 3 - Medium | Resolved | As Built Tabular data icon issue - Export is blue and remaining is black | Gireesh Areekkal | 10/26/2021 12:03 PM | Gireesh Areekkal | 10/22/2021 2:30 PM |  | ETP\IEP Sprint-02
11626 |  | 2 | 3 - Medium | Resolved | DEV SERVER _ BDR/DDR _ ISSUES WITH AREA FIELD | Aswin Sreesh | 10/26/2021 12:02 PM | Aswin Sreesh | 10/16/2021 3:10 PM | 3.3.2.7 | ETP\IEP-3.3.2.6
10694 |  | 2 | 2 - High | Resolved | TPO- Actual-Internal - Data mismatch | Reshmimol K.K. | 10/26/2021 11:09 AM | Reshmimol K.K. | 5/28/2021 4:22 PM | 3.3.2.13(28-May) | ETP\IEP-3.3.2.1 Development Release
11466 | 1981324679 | 2 | 3 - Medium | Resolved | ITT_ RR EMST_ Mismatch in the column name and item is missing in the action item notification. | Aneesha Chandramohan | 10/26/2021 10:04 AM | Aneesha Chandramohan | 2021-02-10 19:20 | 3.3.2.51 | ETP\IEP-3.3.2.4
10581 |  | 2 | 3 - Medium | Resolved | Dev server - Quality - COQ- ENG CoQ and All CoQ tabular export not completed even after 20 minutes when selected All Contracts. However, it worked for My Contracts. | Reshmimol K.K. | 10/19/2021 7:51 PM | Reshmimol K.K. | 2021-12-05 17:54 | 3.3.1.88 (12-May) | ETP\IEP-3.3.2.0
10582 |  | 2 | 2 - High | Resolved | Dev server - COQ - Cost column in $ not available for FM tabular in exported excel file. (both in ENG COQ and All COQ) | Reshmimol K.K. | 10/19/2021 7:50 PM | Reshmimol K.K. | 5/13/2021 6:35 AM | 3.3.1.88 (12-May) | ETP\IEP-3.3.2.0
11635 |  | 2 | 3 - Medium | Resolved | Devserver - ISPO/VDR - OTR trend - Columns are not displaying based on selection in tabular data (especially Issue number and Revision number) | Reshmimol K.K. | 10/19/2021 5:39 PM | Reshmimol K.K. | 10/19/2021 5:18 PM | 3.3.2.7 | ETP\IEP-3.3.2.6
11622 |  | 3 | 3 - Medium | Resolved | Extra blank sheets are displaying in tabular data export file | Jeetu James | 10/19/2021 5:22 PM | Jeetu James | 10/15/2021 10:59 PM | 3.3.2.7 | ETP\IEP-3.3.2.6
10583 |  | 2 | 3 - Medium | Resolved | Dev server -ECN- The page number is not visible completely when page number is 4 digits like 2888. | Reshmimol K.K. | 10/19/2021 5:13 PM | Reshmimol K.K. | 5/13/2021 6:39 AM | 3.3.1.88 (12-May) | ETP\IEP-3.3.2.0
11587 |  | 2 | 3 - Medium | Resolved | Dev server _ System DR1 _ The picture for thumbnail files other than image files. | Aswin Sreesh | 10/19/2021 4:57 PM | Aswin Sreesh | 2021-09-10 22:07 | 3.3.2.6 | ETP\IEP-3.3.2.6
11585 |  | 2 | 3 - Medium | Resolved | DEV SERVER_ SYSTEM DR1 _ Alignment of evidence pic in exported excel file. | Aswin Sreesh | 10/19/2021 4:56 PM | Aswin Sreesh | 2021-09-10 21:52 | 3.3.2.6 | ETP\IEP-3.3.2.6
11620 |  | 2 | 3 - Medium | Resolved | Dev server - Observation - VDR- the data is not correct in the exported file | Reshmimol K.K. | 10/19/2021 4:49 PM | Reshmimol K.K. | 10/15/2021 9:18 PM | 3.3.2.7 | ETP\IEP-3.3.2.6
11517 |  | 2 | 3 - Medium | Resolved | Engineering -Tools - Right click a tool shows one option such as 'Work Offline' . Remove this option . There is no ''Work Offline" functionality in IEP | Gireesh Areekkal | 10/19/2021 1:08 PM | Gireesh Areekkal | 2021-08-10 13:07 |  | ETP\IEP-3.3.2.1 Development Release
11398 |  | 2 | 3 - Medium | Resolved | IEP-Sanity test- UI issues | Reshmimol K.K. | 10/19/2021 10:12 AM | Reshmimol K.K. | 9/16/2021 7:27 PM | 3.3.2.46 | ETP\IEP-3.3.2.4
11497 |  | 2 | 3 - Medium | Resolved | DR-IEP hang on select contract and train in other contract | Bajila Salim | 10/19/2021 10:12 AM | Bajila Salim | 2021-04-10 22:12 |  | ETP\IEP-3.3.2.4
11417 | 1960898679 | 2 | 3 - Medium | Resolved | PE-FPE HandOver - There is no option to identify the newly assigned FPE. | Reshmimol K.K. | 2021-11-10 16:37 | Reshmimol K.K. | 9/28/2021 3:53 PM | 3.3.2.51 | ETP\IEP-3.3.2.4
10696 |  | 4 | 3 - Medium | Resolved | Selected Division and INT/EXT is getting change while do change the hours to quarter and taking grid view also | Reshmimol K.K. | 2021-04-10 14:43 | Jerin K. Thomas | 5/28/2021 4:52 PM |  | ETP\IEP-3.3.2.1 Development Release
10660 |  | 1 | 1 - Critical | Resolved | Grid value is differ from the chart value for demand | Reshmimol K.K. | 2021-04-10 11:22 | Jerin K. Thomas | 5/25/2021 3:23 PM |  | ETP\IEP-3.3.2.1 Development Release
11407 |  | 2 | 3 - Medium | Resolved | Eng runrate - There is a slight data mismatch for platform , product and projects. | Reshmimol K.K. | 2021-01-10 13:52 | Reshmimol K.K. | 9/27/2021 11:05 AM | 3.3.2.5 | ETP\IEP-3.3.2.4
10565 |  | 2 | 3 - Medium | Resolved | DR UI- Suggestion- If the popup is not closed when user scrolls vertically, there is no provision for user to identify the popup again. | Reshmimol K.K. | 9/28/2021 2:22 PM | Reshmimol K.K. | 2021-10-05 13:47 | 3.3.1.88(7-May) | ETP\IEP-3.3.2.0
11304 |  | 3 | 3 - Medium | Resolved | Legends overlapping in VDR finalization trend chart | Jeetu James | 9/17/2021 6:12 PM | Jeetu James | 8/31/2021 2:59 PM | 3.3.2.43 | ETP\IEP-3.3.2.4
7285 | 1999729280 | 2 | 3 - Medium | Resolved | Technical Alignment -> Entries DE SSO with no value i.e. #VALUE!, displayed in count for some jobs and not displayed in some other jobs | Needu D. | 6/29/2021 5:06 PM | Needu D. | 2019-09-12 12:03 |  | ETP\IEP-3.3.2.0
7420 | 1999991502 | 2 | 3 - Medium | Resolved | PT - Performance issue - Sometime/Very few times it take time to load settings pop window | Needu D. | 6/29/2021 5:06 PM | Needu D. | 1/17/2020 4:14 PM | IEP - 3.2.6.1 | ETP\IEP-3.3.2.0
6849 | 1999990653 | 2 | 3 - Medium | Resolved | IEP- Italian Language option is not implemented in phase 3. Please check. | Rashmi K.P | 6/29/2021 5:06 PM | Rashmi K.P | 2019-02-08 17:27 |  | ETP\IEP-3.3.2.0
7050 | 888888888 | 2 | 3 - Medium | Resolved | Hive NCR -> 2018 Data - Imputation code 039 is not added in Bernocchi | Needu D. | 6/29/2021 5:06 PM | Needu D. | 2019-11-10 14:53 |  | ETP
6422 | 1999633342 | 2 | 3 - Medium | Resolved | Engineering Dashboard - MOM - Action item count showing wrong under train.But not in project level selection.(Refer attachment) | Ninan C. Joseph | 6/29/2021 5:06 PM | Ninan C. Joseph | 4/16/2019 3:08 PM |  | ETP\IEP-3.3.2.0
6575 | 1999972477 | 2 | 2 - High | Resolved | Project Management- Manually added projects are not getting added to the project list. Unable to search or track the project. Please check. | Rashmi K.P | 6/29/2021 5:06 PM | Rashmi K.P | 5/31/2019 12:10 PM |  | ETP\IEP-3.3.2.0
6364 | 1999956605 | 2 | 3 - Medium | Resolved | Hive- COQ- Without having TDQuality file, in the Tabular section, 'RedeignLC' data is displaying. After uploading the TDQuality file, the tabular data for LC office is not displaying. | Rashmi K.P | 6/29/2021 5:06 PM | Rashmi K.P | 3/27/2019 5:45 PM |  | ETP
4408 | 1000000000 | 2 | 3 - Medium | Resolved | [IEP Client] - Scrolling is not possible using mouse, in most of the discipline combo box | Reshmimol K.K. | 6/29/2021 5:06 PM | Reshmimol K.K. | 2018-07-02 16:57 |  | ETP\ETP-Sprint-26
4415 | 500000000 | 2 | 3 - Medium | Resolved | [IEP-client] - Tab order is not not set properly in the application | Reshmimol K.K. | 6/29/2021 5:06 PM | Reshmimol K.K. | 2018-08-02 12:21 |  | ETP\ETP-Sprint-26
10599 |  | 2 | 2 - High | Resolved | Production server - when selected KPI tab in quality, application has exited automatically. It occurred sometimes | Reshmimol K.K. | 5/15/2021 7:54 PM | Reshmimol K.K. | 5/15/2021 6:55 PM | 3.3.2.0 | ETP\IEP-3.3.2.0
10315 |  | 2 | 3 - Medium | Resolved | Dev server - NPD - Togo - Some issues when LE file is in one quarter and actual and committed file is in another quarter. | Reshmimol K.K. | 5/15/2021 7:23 PM | Reshmimol K.K. | 2021-01-04 23:59 | 3.3.1.84 (1-Apr-2021) | ETP\IEP-3.3.2.0
10416 |  | 2 | 2 - High | Resolved | NCM data analytics- Dev server - When select Ashok Rodagi from change the dashboard , the graph is not displayed. - Performance issue | Reshmimol K.K. | 4/28/2021 7:43 PM | Reshmimol K.K. | 4/27/2021 1:03 PM | 3.3.1.87(26-Apr) | ETP\IEP-3.3.2.0
10415 |  | 2 | 3 - Medium | Resolved | Suggestion- NCM data analytics - If there is no data available for particular filter, show a message like "data not found" similar in other tools. | Reshmimol K.K. | 4/28/2021 10:04 AM | Reshmimol K.K. | 4/27/2021 11:46 AM | 3.3.1.87 (26-Apr) | ETP\IEP-3.3.2.0
10410 |  | 2 | 3 - Medium | Resolved | BH tool - The tool privilege is not working as expected | Reshmimol K.K. | 4/27/2021 12:56 PM | Reshmimol K.K. | 4/26/2021 6:28 PM | 3.3.1.87 (26-Apr) | ETP\IEP-3.3.2.0
10414 |  | 2 | 3 - Medium | Resolved | NCm data analytics - server failed error occured when click on apply button. | Reshmimol K.K. | 4/27/2021 12:50 PM | Reshmimol K.K. | 4/27/2021 11:32 AM | 3.3.1.87 (26-Apr) | ETP\IEP-3.3.2.0
10411 |  | 2 | 2 - High | Resolved | BH tool - Scheduler functionality is not implemented. | Reshmimol K.K. | 4/26/2021 8:01 PM | Reshmimol K.K. | 4/26/2021 6:31 PM | 3.3.1.87 (26-Apr) | ETP\IEP-3.3.2.0
10408 |  | 2 | 3 - Medium | Resolved | BH tool - If new version of tool exist in the configured folder, it may not fetch since the configured file only fetched from the folder. | Reshmimol K.K. | 4/26/2021 5:08 PM | Reshmimol K.K. | 4/26/2021 4:50 PM | 3.3.1.87 (26-Apr) | ETP\IEP-3.3.2.0
10361 |  | 2 | 3 - Medium | Resolved | NCM data analytics - There is no provision to view the status of new file processing after re-train ML module in IEP. | Reshmimol K.K. | 4/15/2021 11:23 AM | Reshmimol K.K. | 2021-09-04 14:18 | 3.3.1.84(9-Apr) | ETP\IEP-3.3.2.0
10285 |  | 1 | 2 - High | Resolved | Quality Hive: Huge data mismatch with inflow outflow data for TMS -Responsiveness | Ambili K.J. | 2021-11-04 11:15 | Ambili K.J. | 3/30/2021 12:30 PM |  | ETP\IEP-3.3.2.0
10380 |  | 2 | 3 - Medium | Resolved | Quality Hive: Separate tabular data is coming for TPS ENG and TPS DR APPROVER | Ambili K.J. | 2021-10-04 21:24 | Ambili K.J. | 2021-10-04 21:24 |  | ETP\IEP-3.3.2.0
10293 |  | 1 | 2 - High | Resolved | Quality Hive: RCA data from HIVE web and then HIVE in IEP to be considered, pls update latest file for validation with bug fix as discussed for HIVE and same to be implemented in IEP | Ambili K.J. | 2021-10-04 19:58 | Ambili K.J. | 3/30/2021 12:39 PM |  | ETP\IEP-3.3.2.0
10185 |  | 2 | 3 - Medium | Resolved | NCM data analytics- Discipline chart - Cost and blank values is not displayed in pop up | Reshmimol K.K. | 2021-10-04 16:30 | Reshmimol K.K. | 3/22/2021 5:15 PM |  | ETP\IEP-3.3.2.0
9896 |  | 2 | 3 - Medium | Resolved | DR - BDR : Statistics GUI Issues | Meenu Murali | 2021-10-04 15:58 | Meenu Murali | 2/15/2021 9:15 AM | 3.3.1.6(11 Feb 2021) | ETP\IEP-3.3.2.0
10354 |  | 2 | 3 - Medium | Resolved | NCM data analytics - tabular - Correct the alignment of data in all columns to view the data completely. | Reshmimol K.K. | 2021-09-04 22:55 | Reshmimol K.K. | 2021-08-04 21:32 | 3.3.1.84 (8-Apr) | ETP\IEP-3.3.2.0
10122 |  | 2 | 3 - Medium | Resolved | Dev server - project summary - Eng progress (page 6) - while import the file, error message displayed that datetime is not correct | Reshmimol K.K. | 2021-09-04 20:45 | Reshmimol K.K. | 3/16/2021 10:06 PM | 3.3.1.82 | ETP\IEP-3.3.2.0
10347 |  | 2 | 3 - Medium | Resolved | NCM analytics - Individual - invalid machine model displayed in the filter. | Reshmimol K.K. | 2021-09-04 20:33 | Reshmimol K.K. | 2021-08-04 13:29 | 3.3.1.84 (8-apr) | ETP\IEP-3.3.2.0
9523 | 1930769158 | 2 | 3 - Medium | Resolved | Eng run rate - Suggestion - Change the calendar management design would be more user friendly. | Reshmimol K.K. | 2021-09-04 20:31 | Reshmimol K.K. | 2021-08-01 14:38 | 3.3.1.6(7-Jan) | ETP\IEP-3.3.2.0
9502 | 1882051220 | 2 | 3 - Medium | Resolved | Open SWL - Displayed unwanted value in UI | Reshmimol K.K. | 2021-09-04 20:30 | Reshmimol K.K. | 2021-04-01 18:28 |  | ETP\IEP-3.3.2.0
9901 |  | 2 | 3 - Medium | Resolved | Change Request - NPD-Eng run rate - Adding past fiscal weeks value in grid. The values to be taken from actual file. | Reshmimol K.K. | 2021-09-04 20:30 | Reshmimol K.K. | 2/15/2021 12:48 PM | 3.3.1.6 | ETP\IEP-3.3.2.0
9512 | 1907692240 | 2 | 2 - High | Resolved | Eng run rate - When only one day is selected for Togo, the Day average is expected to be displayed as Togocost. But data mismatch is there. | Reshmimol K.K. | 2021-09-04 20:29 | Reshmimol K.K. | 2021-07-01 19:13 | 3.3.1.6(7-Jan) | ETP\IEP-3.3.2.0
10321 |  | 2 | 2 - High | Resolved | DR - Unable to enter Discussion Details in Checklist | Meenu Murali | 2021-09-04 19:30 | Meenu Murali | 2021-05-04 19:19 | 3.3.1.84(05 April 2021) | ETP\IEP-3.3.2.0
10341 |  | 2 | 3 - Medium | Resolved | Quality -Hive - change the data not available message | Reshmimol K.K. | 2021-09-04 18:44 | Reshmimol K.K. | 2021-08-04 09:54 | 3.3.1.82 (2-Apr) | ETP\IEP-3.3.2.0
10363 |  | 2 | 3 - Medium | Resolved | NCM data analytics - 1106267 project is not available in IEP, but NCM count is available for this project. This job available in data correction data. | Reshmimol K.K. | 2021-09-04 18:30 | Reshmimol K.K. | 2021-09-04 16:14 | 3.3.1.84 (8-Apr) | ETP\IEP-3.3.2.0
10365 |  | 2 | 3 - Medium | Resolved | NCM data analytics - After searching any field which column places in middle of tabular, the scroll bar automatically move to end of the tabular. | Reshmimol K.K. | 2021-09-04 18:16 | Reshmimol K.K. | 2021-09-04 17:05 | 3.3.1.84 (9-Apr) | ETP\IEP-3.3.2.0
10360 |  | 2 | 3 - Medium | Resolved | HC Mapping - Latest Input files: HC Mapping not taking latest mapping file after scheduling in control panel | Reshmimol K.K. | 2021-09-04 16:17 | Harish G. | 2021-09-04 13:34 |  | ETP\IEP-3.3.2.0
10345 |  | 2 | 3 - Medium | Resolved | App lead - Monthly trend calculation logic issue when the CY1 is negative value and CY2 is positive value. | Reshmimol K.K. | 2021-09-04 12:05 | Reshmimol K.K. | 2021-08-04 12:20 | 3.3.1.84 (8-Apr) | ETP\IEP-3.3.2.0
10346 |  | 2 | 3 - Medium | Resolved | App lead - Monthly trend - equal sign is displayed when selected the month as January. But monthly trend of remaining parameters displayed as NA. | Reshmimol K.K. | 2021-09-04 10:27 | Reshmimol K.K. | 2021-08-04 12:22 | 3.3.1.84 (8-Apr) | ETP\IEP-3.3.2.0
10106 |  | 2 | 3 - Medium | Resolved | DR - DDR/BDR - Action owner selection shall include also a dropdown (only the names of the people selected for pre-work) | Gireesh Areekkal | 2021-08-04 17:32 | Gireesh Areekkal | 2021-10-03 17:43 |  | ETP\IEP-3.3.2.0
9652 |  | 2 | 3 - Medium | Resolved | NCM tabular data flickering on loading the OFFICE data | Gireesh Areekkal | 2021-08-04 11:51 | Gireesh Areekkal | 1/21/2021 1:44 PM |  | ETP\IEP-3.3.2.0
10312 |  | 2 | 3 - Medium | Resolved | As-Built - Sort Functionality for some Tabular columns are not working properly. (Say, Doc#, Document status) | Meenu Murali | 2021-01-04 19:15 | Meenu Murali | 2021-01-04 12:40 | 3.3.1.83(31 march 2021) | ETP\IEP-3.3.2.0
10209 |  | 2 | 3 - Medium | Resolved | As Built - Add documents option not required for Focal dashboard | Gireesh Areekkal | 2021-01-04 19:06 | Gireesh Areekkal | 3/23/2021 3:20 PM |  | ETP\IEP-3.3.2.0
10307 |  | 2 | 3 - Medium | Resolved | Eng run rate - FW1 data is not displaying in the tabular. Is it required to display as value 0. | Reshmimol K.K. | 2021-01-04 16:56 | Reshmimol K.K. | 3/31/2021 3:04 PM | 3.3.1.83(29-Mar) | ETP\IEP-3.3.2.0
10306 |  | 2 | 3 - Medium | Resolved | Eng Run rate - Change the fiscal week number | Reshmimol K.K. | 2021-01-04 16:55 | Reshmimol K.K. | 3/31/2021 2:57 PM | 3.3.1.83(30-Mar) | ETP\IEP-3.3.2.0
10305 |  | 2 | 3 - Medium | Resolved | Eng run rate - Actual cost and Togo cost is not correct | Reshmimol K.K. | 2021-01-04 16:52 | Reshmimol K.K. | 3/31/2021 2:50 PM | 3.3.1.83 (30-Mar) | ETP\IEP-3.3.2.0
10271 | 1997997998 | 2 | 3 - Medium | Resolved | CAD- Hours summary - Unwanted decimal points are added in UI. | Reshmimol K.K. | 3/30/2021 1:22 PM | Reshmimol K.K. | 3/28/2021 7:48 PM | 3.3.1.32(25-Mar) | ETP\IEP-3.3.2.0
9441 | 1975975976 | 2 | 3 - Medium | Resolved | JOT-No popup message shown for some Job categorization(when the value is very small) | Reshmimol K.K. | 3/29/2021 10:11 AM | Reshmimol K.K. | 12/18/2020 9:29 PM | IEP v3.3.1.2 JOT | ETP\IEP-3.3.2.0
9451 | 1977977978 | 2 | 3 - Medium | Resolved | JOT/General - Scale used in y-axis is different in chart and exported excel | Reshmimol K.K. | 3/29/2021 10:11 AM | Reshmimol K.K. | 12/19/2020 8:46 PM | IEP v3.3.1.2 | ETP\IEP-3.3.2.0
9460 | 1981314648 | 2 | 3 - Medium | Resolved | TechInnv - Graph - Order of legends and the bars is not in same as in SRS . | Reshmimol K.K. | 3/29/2021 10:11 AM | Reshmimol K.K. | 12/21/2020 7:39 PM | IEP v3.3.1.2 (20-Dec) | ETP\IEP-3.3.2.0
10089 |  | 2 | 3 - Medium | Resolved | Project Summary - Color scheme is not saving in other pages when value is empty in executive summary page | Reshmimol K.K. | 2021-12-03 16:29 | Reshmimol K.K. | 2021-08-03 15:53 | 3.3.1.81(Mar-8) | ETP\IEP-3.3.2.0
10063 |  | 2 | 3 - Medium | Resolved | CAD- Select Actual Percentage and filter on Ref Month %, CY Total is got updated according filter so Percentage is always 100% | Brilsa Raj | 2021-10-03 10:28 | Brilsa Raj | 2021-04-03 11:47 |  | ETP
10029 |  | 2 | 3 - Medium | Resolved | Project summary- EPR action items- Not visible the column name completely. | Reshmimol K.K. | 2021-08-03 11:38 | Reshmimol K.K. | 2021-03-03 12:03 | 3.3.1.18 | ETP\IEP-3.3.2.0
10082 |  | 2 | 3 - Medium | Resolved | CAD- CY Percentage is always 100 when CY Total and CY Selected for All Categories | Brilsa Raj | 2021-04-03 19:25 | Brilsa Raj | 2021-04-03 18:56 |  | ETP\IEP-3.3.2.0
10080 |  | 2 | 3 - Medium | Resolved | CAD- Requirement to apply formula to consolidate P&M , P&M HOU, P&M WB in one team | Brilsa Raj | 2021-04-03 19:22 | Brilsa Raj | 2021-04-03 18:55 |  | ETP\IEP-3.3.2.0
10017 | 1997435898 | 2 | 3 - Medium | Resolved | Dev server - Open SWL - GT-ST data mismatch (LE- 11-1, committed today - 03-02) | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 2/27/2021 12:33 PM | 3.3.1.18 | ETP\IEP-3.3.2.0
9486 | 1853846098 | 2 | 2 - High | Resolved | Open SWL- Value of Open is different based on customer pivot and in the IEP application. | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 12/23/2020 3:04 PM | 3.3.1.6 (23-Dec) | ETP\IEP-3.3.2.0
9487 | 1856410200 | 2 | 3 - Medium | Resolved | Open SWL - rounding issue is there | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 12/23/2020 5:05 PM | 3.3.1.6 (22-Dec) | ETP\IEP-3.3.2.0
9488 | 1858974302 | 2 | 3 - Medium | Resolved | Open SWL- Observation - Sum of Secure and Open is getting as analyzed committed open for certain platforms, products, projects | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 12/23/2020 5:32 PM | 3.3.1.6(22-Dec) | ETP\IEP-3.3.2.0
9494 | 1874358914 | 2 | 3 - Medium | Resolved | Open SWL- The columns Confirmed, Maybe, Open, Lost is not displayed in grid. | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 12/28/2020 9:46 AM | 3.3.1.6 (24-Dec) | ETP\IEP-3.3.2.0
9339 | 1615384612 | 2 | 2 - High | Resolved | S-Curve - chart view- LE value and LE cumulated in first quarter should be same | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 2020-01-12 16:18 | 3.3.1.2 | ETP\IEP-3.3.2.0
9381 | 1669230754 | 2 | 3 - Medium | Resolved | Observation - S-curve - Data validation - number rounding issue is observed. | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 2020-07-12 14:33 | 3.3.1.4 | ETP\IEP-3.3.2.0
9399 | 1707692284 | 2 | 2 - High | Resolved | Open SWL- Value of potential open is mismatch | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 2020-11-12 13:21 | 3.3.1.6 | ETP\IEP-3.3.2.0
9410 | 1735897406 | 2 | 3 - Medium | Resolved | ToGo - Value in grid and chart is not matching | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 12/14/2020 6:00 PM | 3.3.1.6 (14-Dec) | ETP\IEP-3.3.2.0
9412 | 1741025610 | 3 | 3 - Medium | Resolved | SWL - Roundoff mismatch issue for LE, cumulative. | Jeetu James | 2021-04-03 14:24 | Jeetu James | 12/15/2020 10:23 AM | 3.3.1.6 | ETP\IEP-3.3.2.0
9416 | 1751282018 | 2 | 2 - High | Resolved | ToGo - graph - negative values are not displayed (even in tooltip). | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 12/15/2020 11:55 AM | 3.3.1.6 (14-Dec) | ETP\IEP-3.3.2.0
9458 | 1830769180 | 2 | 3 - Medium | Resolved | Observation - togo- Total value of covered in UI - Rounding issue | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 12/21/2020 10:27 AM | 3.3.1.6 (20-Dec) | ETP\IEP-3.3.2.0
9531 | 1941025566 | 2 | 3 - Medium | Resolved | Eng run rate - Rounding Issue | Reshmimol K.K. | 2021-04-03 14:24 | Reshmimol K.K. | 2021-09-01 17:49 | 3.3.1.6 (9-Jan) | ETP\IEP-3.3.2.0
9985 |  | 3 | 3 - Medium | Resolved | Dev - DR -BDR - On changing the dead line date to 10-Mar-2021, it is automatically changed to 07-Apr-2021 | Jeetu James | 2/22/2021 1:05 PM | Jeetu James | 2/22/2021 11:32 AM | 3.3.1.8 | ETP\IEP-3.3.2.0
9984 |  | 3 | 3 - Medium | Resolved | Dev -DR -Overall performance in dev server is slow | Jeetu James | 2/22/2021 1:04 PM | Jeetu James | 2/22/2021 11:31 AM | 3.3.1.8 | ETP\IEP-3.3.2.0
9860 |  | 2 | 3 - Medium | Resolved | As -built :- When delete any of the rows after a search, it still displaying till the next search/update. And the search column is in fixed size | Reshmimol K.K. | 2021-10-02 20:12 | Reshmimol K.K. | 2021-10-02 20:10 | 3.3.1.6 (10-Feb) -2nd | ETP\IEP-3.3.2.0
9836 |  | 2 | 3 - Medium | Resolved | As-built :- Editable fieldcan not be identified easily by user | Reshmimol K.K. | 2021-09-02 19:50 | Reshmimol K.K. | 2021-08-02 15:43 | 3.3.1.6 (8-Feb) | ETP\IEP-3.3.2.0
9787 |  | 3 | 3 - Medium | Resolved | Hive - COQ - Details graph - Chart showing in exported excel is not correct | Jeetu James | 2021-09-02 17:03 | Jeetu James | 2021-05-02 13:01 | 3.3.1.6 | ETP\IEP-3.3.2.0
9837 |  | 2 | 3 - Medium | Resolved | As built - suggestion - It would be good to add History information. So that user can identify the previous users in the workflow with date | Reshmimol K.K. | 2021-09-02 09:48 | Reshmimol K.K. | 2021-08-02 16:18 | 3.3.1.6 (8-Feb) | ETP\IEP-3.3.2.0
9696 |  | 3 | 3 - Medium | Resolved | RCA CAPA - Scroll and searched column is missing when search data is blank | Jeetu James | 2021-02-02 09:09 | Jeetu James | 2021-01-02 12:40 | 3.3.1.6 | ETP\IEP-3.3.2.0
9621 |  | 2 | 3 - Medium | Resolved | Observation - PT scheduler execution status shows as 1 days 1 hours 33 minutes and not able to execute the PT scheduler. | Reshmimol K.K. | 1/18/2021 11:35 AM | Reshmimol K.K. | 1/17/2021 8:26 PM | 3.3.1.6 (16-Jan) | ETP\IEP-3.3.2.0
9596 | 1966666658 | 2 | 2 - High | Resolved | ISPO - Spinner keeps on loading on clicking total documents after selecting all contracts | Jeetu James | 1/15/2021 11:30 PM | Jeetu James | 1/14/2021 12:45 PM | 3.3.1.6 | ETP\IEP-3.3.2.0
9599 | 1991666657 | 3 | 3 - Medium | Resolved | Tabular Data Sorting - MOM/Hazop/3D Review- Sorting is not displaying properly on selecting different pagination. | Jeetu James | 1/15/2021 11:30 PM | Jeetu James | 1/14/2021 5:29 PM | 3.3.1.6 | ETP\IEP-3.3.2.0
9188 | 148148148 | 3 | 3 - Medium | Resolved | Tech Innv - Year and month filter is not displayed for data by team drop down | Jeetu James | 11/25/2020 12:09 PM | Jeetu James | 10/14/2020 6:20 PM | 3.3.0.9 | ETP\IEP-3.3.2.0
9208 | 567901234 | 2 | 3 - Medium | Resolved | Observation - Currency of some values are displayed as USD instead of Euro in input file. But for calculation it as considered as Euro | Reshmimol K.K. | 11/25/2020 12:09 PM | Reshmimol K.K. | 10/15/2020 4:58 PM | IEP v3.3.0.9 (15-Oct) | ETP\IEP-3.3.2.0
9209 | 592592592 | 2 | 3 - Medium | Resolved | JOT Closed Current Year & Delivered-Ongoing (K€) - Popup should be displayed even a small number is for particular status. | Reshmimol K.K. | 11/25/2020 12:09 PM | Reshmimol K.K. | 10/15/2020 5:16 PM | IEP v3.3.0.9 (15-Oct) | ETP\IEP-3.3.2.0
9210 | 617283950 | 2 | 3 - Medium | Resolved | JOT Closed Current Year & Delivered-Ongoing (K€) - Follow the same order in both chart and tool tip - applicable to other charts as well | Reshmimol K.K. | 11/25/2020 12:09 PM | Reshmimol K.K. | 10/15/2020 5:28 PM | IEP v3.3.0.9 (15-Oct) | ETP\IEP-3.3.2.0
9211 | 641975308 | 2 | 3 - Medium | Resolved | Observation - JOT Closed Current Year & Delivered-Ongoing (K€) - Color combination of graph is different in exported file | Reshmimol K.K. | 11/25/2020 12:09 PM | Reshmimol K.K. | 10/15/2020 5:31 PM | IEP v3.3.0.9 (15-Oct) | ETP\IEP-3.3.2.0
9246 | 1086419752 | 4 | 4 - Low | Resolved | CAD - CAPACITY-ACTUALS-DEMAND- ACTUALS % - Search option should be added for each column for user to filter out | Jeetu James | 11/25/2020 12:09 PM | Jeetu James | 10/19/2020 3:54 PM | 3.3.0.9 | ETP\IEP-3.3.2.0
9265 | 1358024690 | 2 | 3 - Medium | Resolved | Observation - CAD-Hours Summary - Issue in rounding the decimal points. | Reshmimol K.K. | 11/25/2020 12:09 PM | Reshmimol K.K. | 10/23/2020 7:03 PM | IEP v3.3.0.9 (23-Oct)_5:30pm | ETP\IEP-3.3.2.0
9295 |  | 2 | 3 - Medium | Resolved | Suggestion - Populating filter used in excel output for easy reference. | Reshmimol K.K. | 2020-12-11 17:56 | Reshmimol K.K. | 2020-11-11 10:12 | 3.3.1.0 | ETP\IEP-3.3.2.0
9272 |  | 3 | 3 - Medium | Resolved | Rulestream usage dashboard - Classification chart - Remove decimal values in pie chart tool tip for classification count. | Jeetu James | 10/30/2020 7:23 PM | Jeetu James | 10/29/2020 11:05 AM | 3.3.0.9 | ETP\IEP-3.3.2.0
7637 | 1999994049 | 3 | 4 - Low | Resolved | IEP - Drop down list is moving while scrolling the page. | Jeetu James | 2020-12-10 09:57 | Jeetu James | 2/19/2020 12:05 PM | 3.2.7.2 | ETP\IEP-3.3.2.0
7714 |  | 2 | 4 - Low | Resolved | PT - Headings get disappeared while scrolling. It should be freezed the top | Needu D. | 2020-12-10 09:57 | Needu D. | 2020-05-03 10:57 | 3.2.7.1 | ETP\IEP-3.3.2.0
7839 |  | 2 | 4 - Low | Resolved | IEP UI issues when its window size is reduced. | Needu D. | 2020-12-10 09:57 | Needu D. | 3/26/2020 3:19 PM | 3.2.7.7_1 | ETP\IEP-3.3.2.0
7919 |  | 2 | 3 - Medium | Resolved | IEP - Workload chart - Export failed for larger data | Gireesh Areekkal | 2020-12-10 09:57 | Gireesh Areekkal | 2020-08-04 09:31 |  | ETP\IEP-3.3.2.0
7973 |  | 2 | 4 - Low | Resolved | Observation - Software update cannot be done for IEP internal release with version number 3.2.7.10 or greater | George Jerin | 2020-12-10 09:57 | Needu D. | 4/27/2020 10:53 AM | 3.2.7.10 | ETP\IEP-3.3.2.0
8066 |  | 2 | 4 - Low | Resolved | TA - Tabular - Usability issues - After sorting the horizontal bar moves right end. And for another field in right end, vertical scroll bar moves to left side [dev server] | Needu D. | 2020-12-10 09:57 | Needu D. | 5/30/2020 11:04 AM | 3.2.8.2 | ETP\IEP-3.3.2.0
8258 | 181818180 | 2 | 4 - Low | Resolved | Usability issue - Login page - Cursor not viewable since it is in black color. Also sometimes clicking inside password box, it not getting selected andcursor not coming | Needu D. | 2020-12-10 09:57 | Needu D. | 2020-11-06 13:54 | 3.2.8.9 | ETP\IEP-3.3.2.0
8273 | 90899556 | 2 | 3 - Medium | Resolved | My Contracts - Expanded contract getting auto closed after scrolling. Also scroll not smooth sometime. Feels like jumping to from top to bottom or vice versa. | Needu D. | 2020-12-10 09:57 | Needu D. | 6/15/2020 1:03 PM | 3.2.8.9 | ETP\IEP-3.3.2.0
8282 | 1909090910 | 2 | 3 - Medium | Resolved | IEP ped - ccm ncm - close trend - if there is a month with 1 count satisfying the new rule ‘u_fast_containment = yes’, there is no option in chart to click it and view it in tabular | Needu D. | 2020-12-10 09:57 | Needu D. | 6/16/2020 8:25 PM | 3.2.8.9 | ETP\IEP-3.3.2.0
8128 |  | 2 | 4 - Low | Resolved | Project Info Train – Some times if the train is in the bottom of screen, if we click train edit button, scrolling to down instead of edit pop up | Needu D. | 2020-12-10 09:57 | Needu D. | 2020-03-06 12:09 | 3.2.8.2 | ETP\IEP-3.3.2.0
8130 |  | 2 | 3 - Medium | Resolved | IEP-Operation-ISPO-Reassign - reassign notification is not sent to project engineer when the project engineer is not available for selected job number. | Reshmimol K.K. | 2020-12-10 09:57 | Reshmimol K.K. | 2020-03-06 12:19 | 3.2.8.2 | ETP\IEP-3.3.2.0
8146 |  | 2 | 3 - Medium | Resolved | IEP-Operation-VDR- Resource name displayed in a different manner for the same SSOID | Reshmimol K.K. | 2020-12-10 09:57 | Reshmimol K.K. | 2020-04-06 11:46 | 3.2.8.2 | ETP\IEP-3.3.2.0
8110 |  | 2 | 3 - Medium | Resolved | IEP-Quality Tools- Charts- Year-Month format is not uniform | Reshmimol K.K. | 2020-12-10 09:57 | Reshmimol K.K. | 2020-02-06 12:57 | 3.2.8.2 | ETP\IEP-3.3.2.0
8351 |  | 3 | 3 - Medium | Resolved | IEP - Scheduler - SSO profile update scheduler is not updating profile ids in IEP | Jeetu James | 2020-12-10 09:57 | Jeetu James | 6/26/2020 4:11 PM | 3.2.8.9 | ETP\IEP-3.3.2.0
8381 |  | 2 | 3 - Medium | Resolved | Missing resource notification - Without clicking save, all changes made are saved in the Scheduler if we navigate to other pages and come back to this section | Needu D. | 2020-12-10 09:57 | Needu D. | 2020-02-07 10:14 | 3.2.8.9 | ETP\IEP-3.3.2.0
8388 |  | 2 | 2 - High | Resolved | After IEP logged in for long hours without any activity (kept online for overnight), no data loaded in ispo/vdr/vdr rev/ta/mom etc., no menu items in scheduler and iep crashes after some clicks | Needu D. | 2020-12-10 09:57 | Needu D. | 2020-03-07 09:09 | 3.2.8.9 | ETP\IEP-3.3.2.0
8502 |  | 2 | 3 - Medium | Resolved | IEP- Control panel - Project management - Meeting - Usability Issue | Reshmimol K.K. | 2020-12-10 09:57 | Reshmimol K.K. | 2020-08-07 13:09 | 3.2.8.9 | ETP\IEP-3.3.2.0
8609 |  | 2 | 3 - Medium | Resolved | Observation - Scheduler - user does not have any intimation when any of the scheduled job is failed. | Reshmimol K.K. | 2020-12-10 09:57 | Reshmimol K.K. | 7/16/2020 5:27 PM | 3.2.9.1 | ETP\IEP-3.3.2.0
8192 |  | 2 | 3 - Medium | Resolved | IEP-Dashboard- It would be good to add collapse/expand option for primary projects too similar for secondary project (suggestion) | Reshmimol K.K. | 2020-12-10 09:57 | Reshmimol K.K. | 2020-10-06 11:03 | 3.2.8.6 | ETP\IEP-3.3.2.0
8112 |  | 2 | 3 - Medium | Resolved | ISPO - Auto assigned - Instead of 2 person, total 4 sso i.e wrong 2 more sso are displayed in auto assigned | Needu D. | 2020-12-10 09:57 | Needu D. | 2020-02-06 13:57 | 3.2.8.2 | ETP\IEP-3.3.2.0
8532 |  | 2 | 3 - Medium | Resolved | IEP- TA- PO schedule Date is not found in input file | Reshmimol K.K. | 2020-12-10 09:57 | Reshmimol K.K. | 2020-09-07 18:05 | 3.2.9.1 | ETP\IEP-3.3.2.0
8586 |  | 2 | 4 - Low | Resolved | Productivity Tracker - All Contracts - Disp view - Loading taking long time and application jerks while loading it. No issue with my contract disp view. | Needu D. | 2020-12-10 09:57 | Needu D. | 7/15/2020 10:44 AM | 3.2.9.2 | ETP\IEP-3.3.2.0
8664 |  | 4 | 4 - Low | Resolved | IEP - Notification window - Once the notification window is minimized, there is no button to maximize the notification window | Jeetu James | 2020-12-10 09:57 | Jeetu James | 7/22/2020 7:03 PM | 3.3.0.0 | ETP\IEP-3.3.2.0
8752 |  | 2 | 3 - Medium | Resolved | Dev server - 4 serial numbers missing for project 1105255-RAS TANURA. Total 12 serial number for this. Only 8 displayed | Needu D. | 2020-12-10 09:57 | Needu D. | 2020-06-08 11:55 | 3.2.9.7 | ETP\IEP-3.3.2.0
8892 |  | 3 | 3 - Medium | Resolved | IEP - Snipping Tool - MOM/Hazop/3D Review - Entire page is not displayed to snip, right side part of screen is not displaying while trying to snip the entire page. | Jeetu James | 2020-12-10 09:57 | Jeetu James | 9/14/2020 4:30 PM | 3.3.0.1 | ETP\IEP-3.3.2.0
9115 |  | 2 | 3 - Medium | Resolved | Observation- when there are multiple realdoc ID associated to same Activity ID. It is not displayed in pareto chart. | Reshmimol K.K. | 2020-12-10 09:57 | Reshmimol K.K. | 2020-07-10 13:48 | 3.3.0.8 | ETP\IEP-3.3.2.0
8471 |  | 3 | 3 - Medium | Resolved | IEP - NPD - Enhancements - LE value for S Curve and LE value for previous LE in graph for Quarter 2 are not matching | Jeetu James | 2020-05-08 17:31 | Jeetu James | 2020-06-07 15:52 | 3.2.8.9 | ETP\IEP-3.3.1.0
8149 |  | 3 | 3 - Medium | Resolved | IEP - NPD Phase2 - Scheduler is showing success message even if the input file format is different | Jeetu James | 2020-05-08 17:31 | Jeetu James | 2020-04-06 16:59 | 3.2.8.4 | ETP\IEP-3.3.1.0
8167 |  | 3 | 3 - Medium | Resolved | IEP - NPD S Curve - Grid view not changing according to the filter selected in S Curve graph. | Jeetu James | 2020-05-08 17:31 | Jeetu James | 2020-08-06 15:36 | 3.2.8.6 | ETP\IEP-3.3.1.0
8136 |  | 3 | 3 - Medium | Resolved | IEP - NPD Phase2 - Actual vs Baseline demand graph - Baseline and updated legends are not displaying under each bar in graph | Jeetu James | 2020-05-08 17:31 | Jeetu James | 2020-03-06 15:15 | 3.2.8.4 | ETP\IEP-3.3.1.0
8118 |  | 2 | 2 - High | Resolved | IEP - NPD Phase2 - Previous LE vs Baseline LE - Total year value for OP, target, actual in graph tool tip is not correct. | Jeetu James | 2020-05-08 17:31 | Jeetu James | 2020-02-06 15:45 | 3.2.8.3 | ETP\IEP-3.3.1.0
8099 |  | 3 | 3 - Medium | Resolved | IEP - NPD Phase2 - Previous LE vs Baseline LE - Next value range in Y axis should be displayed in graph if the value in graph is higher than the displayed range. | Jeetu James | 2020-05-08 17:31 | Jeetu James | 2020-01-06 16:19 | 3.2.8.3 | ETP\IEP-3.3.1.0
8735 |  | 3 | 3 - Medium | Resolved | IEP - NPD Phase4 - Better to add another legend with different colour to specify the forecast average value | Jeetu James | 7/30/2020 2:45 PM | Jeetu James | 7/28/2020 2:47 PM | 3.3.1.0 | ETP\IEP-3.3.1.0

## IEP-Open Issues
ID | Work Item Type | Title | State | Effort | Business Value | Value Area | Tags | Created By | Reason | Assigned To | Found In | Severity
1151 | Bug | ITT :- Support central open action item option window not showing total count items | Resolved |  |  | Business |  | Shreedevi I. Manjari | Fixed | Shreedevi I. Manjari | 3.3.4.2 | 3 - Medium
1283 | Bug | Developer Testing: two tooltip values displayed for bar charts | New |  |  | Business |  | Sreelakshmi R. | New |  |  | 3 - Medium
1284 | Bug | Developer Testing: Loader displayed on selecting result filter from top | New |  |  | Business |  | Sreelakshmi R. | New | Athira V.P. |  | 3 - Medium
1285 | Bug | Developer testing: Excel export filter displayed wrong | New |  |  | Business |  | Sreelakshmi R. | New | Athira V.P. |  | 3 - Medium
1286 | Bug | Developer Testing: Selecting checker values, showing message Ge.Etp.UI.Vi... | New |  |  | Business |  | Sreelakshmi R. | New | Athira V.P. |  | 3 - Medium
1279 | Bug | Developer Testing: IEP crashes on selecting FW chart | New |  |  | Business |  | Sreelakshmi R. | New | Athira V.P. |  | 3 - Medium
1280 | Bug | Developer Testing: Result filter selection issue | New |  |  | Business |  | Sreelakshmi R. | New | Athira V.P. |  | 3 - Medium
1281 | Bug | Developer testing: No data found in FW grid | New |  |  | Business |  | Sreelakshmi R. | New | Athira V.P. |  | 3 - Medium
1282 | Bug | Developer Testing: FW chart not displayed | New |  |  | Business |  | Sreelakshmi R. | New |  |  | 3 - Medium
1263 | Bug | ITT_ Custom CSR_ CSR1 UCP1 details is available in custom CSR. | New |  |  | Business |  | Aneesha Chandramohan | New | Vishal Gaikwad | 3.3.4.23 | 3 - Medium
1265 | Bug | ITT_ CSR_ Only Facilitator can create the custom CSR. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1266 | Bug | ITT_ CSR_ Delete option is not available for custom CSR review. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1267 | Bug | ITT_ CSR_ Creating New CSR with "Copy questions from existing reviews" shows the answers too. | New |  |  | Business |  | Aneesha Chandramohan | New | Vishal Gaikwad | 3.3.4.23 | 3 - Medium
1212 | Bug | ITT_ CSR_Multiple screen is showing while continuously click on the Finish button. | Resolved |  |  | Business |  | Aneesha Chandramohan | Fixed | Aneesha Chandramohan | 3.3.4.23 | 3 - Medium
1224 | Bug | ITT_ CSR_ Pre-work launch for rest of the team member and Launch review option is missing in the checklist. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1225 | Bug | ITT_ CSR_ Error message shows while taking CSR1-UCP1. | Resolved |  |  | Business |  | Aneesha Chandramohan | Fixed | Aneesha Chandramohan | 3.3.4.23 | 3 - Medium
1226 | Bug | ITT_ CSR_ Pre-work assigned team member not able to edit the checklist. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1227 | Bug | ITT_ CSR_ Help info instructions is missing. | Resolved |  |  | Business |  | Aneesha Chandramohan | Fixed | Aneesha Chandramohan | 3.3.4.23 | 3 - Medium
1228 | Bug | ITT_ CSR_ N/A option is missing in dropdown for PM Approval column. | Resolved |  |  | Business |  | Aneesha Chandramohan | Fixed | Aneesha Chandramohan |  | 3 - Medium
1229 | Bug | ITT_CSR_Not able to add the deleted role in the attendence list | Resolved |  |  | Business |  | Minu Mohan | Cannot Reproduce | Minu Mohan | 3.3.4.23 | 3 - Medium
1241 | Bug | ITT_CSR_An error messge and disabled dashboard | Resolved |  |  | Business |  | Minu Mohan | Fixed | Aneesha Chandramohan | 3.3.4.23 | 2 - High
1247 | Bug | ITT_ CSR_ The 3 options popup up is not showing for the team member after starting the review. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1248 | Bug | ITT_ CSR_ Mismatch in column Header Title. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1249 | Bug | ITT_ CSR_ The Questioners should be Left alignment. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1250 | Bug | ITT_CSR_success message is showing without enter the action items. | New |  |  | Business |  | Minu Mohan | New | Nijil M K | 3.3.4.23 | 3 - Medium
1251 | Bug | ITT_CSR_More option is missing in the text field 'Details' | New |  |  | Business |  | Minu Mohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1252 | Bug | ITT_CSR_Discipline column should be available with a dropdown. | New |  |  | Business |  | Minu Mohan | New | Yamuna M S |  | 3 - Medium
1253 | Bug | ITT_ CSR_ Export Report shows failed error message. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1254 | Bug | ITT_ CSR_ The user can submit the review multiple times. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1255 | Bug | ITT_ CSR_ API Failed error popup shows while click on the finish button. | Resolved |  |  | Business |  | Aneesha Chandramohan | Cannot Reproduce | Aneesha Chandramohan | 3.3.4.23 | 1 - Critical
1256 | Bug | ITT_ CSR_ Review submit date not showing in Effective date. | New |  |  | Business |  | Aneesha Chandramohan | New | Vishal Gaikwad | 3.3.4.23 | 3 - Medium
1257 | Bug | ITT_ CSR_ Tool tip is missing in the Status. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1258 | Bug | ITT_ CSR_ Checklist contains an Info icon to show the Scope. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1259 | Bug | ITT_ CSR_ CSR Outcome column is not changing after rejecting the review. | New |  |  | Business |  | Aneesha Chandramohan | New | Vishal Gaikwad | 3.3.4.23 | 3 - Medium
1262 | Bug | ITT _ CSR_ The Reviewer is not able to approve the review notification. | New |  |  | Business |  | Aneesha Chandramohan | New | Vishal Gaikwad | 3.3.4.23 | 2 - High
1264 | Bug | ITT_ CSR_ No option for Disable/Enable the CSR review. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S |  | 3 - Medium
1268 | Bug | ITT_ CSR_ CSR Outcome column should get auto populated. | New |  |  | Business |  | Aneesha Chandramohan | New | Vishal Gaikwad | 3.3.4.23 | 3 - Medium
1269 | Bug | ITT_ CSR_ Mismatch in Pre-work section column name. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1270 | Bug | ITT_ CSR_ N/A option is missing in CSR Residual Risk Column. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1271 | Bug | ITT_ CSR_ Submit popup window contain the ID of action items. | New |  |  | Business |  | Aneesha Chandramohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
1272 | Bug | ITT_CSR_Not able to change action owner in action item checklist | New |  |  | Business |  | Minu Mohan | New | Yamuna M S | 3.3.4.23 | 3 - Medium
234 | Bug | ITT_ There is no popup message showing when the user download the same file twice. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Aneesha Chandramohan | 2.3 version | 3 - Medium
588 | Bug | Dev_Server In Generic DR workflow for manually added DR's download column showing Undefined | Resolved |  |  | Business |  | Shreedevi I. Manjari | Deferred | Shreedevi I. Manjari | 3.3.3.3 | 3 - Medium
841 | Bug | IEP-NPD->Run Rate section->On updating upto April 1st week 2022 file, Togo cost showing wrong | Resolved |  |  | Business |  | Fabian Johnson | Deferred | Bajila Salim | 3.3.3.293 | 2 - High
912 | Bug | Suggestion: While exporting, click on logout button: Highlight the export screen | Resolved |  |  | Business |  | Aparna Raveendran | Deferred | Aparna Raveendran | 3.3.3.35 | 3 - Medium
408 | Bug | IEP->Quality->NCM count issue in Closed trend for Office | Resolved |  |  | Business |  | Fabian Johnson | Deferred | Farhana Begum | 3.3.3.27 | 3 - Medium
1275 | Bug | Production Server:- Copy review :-RR_GT when i tried to copy the trains which has some empty data then it's not taking review submit option | New |  |  | Business |  | Shreedevi I. Manjari | New | Mugesh V. Kannan | 3.3.5.0 | 3 - Medium
1277 | Bug | Approve and Reject button is not working as expected for PE | New |  |  | Business |  | Aparna Raveendran | New | Yamuna M S | 3.3.4.22 | 3 - Medium
1136 | Bug | ITT_ Observation- Blank option is missing in the dropdown for IFC revision number and valid for construction. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Sreelakshmi R. | 3.3.4.1 | 3 - Medium
1140 | Bug | ITT_ Blank selection is showing in real code filter. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Sreelakshmi R. | 3.3.4.1 | 3 - Medium
1093 | Bug | ITT_ Help info not showing any data. | New |  |  | Business |  | Aneesha Chandramohan | New | Amala M R | 3.3.4.1 | 3 - Medium
1139 | Bug | ITT_ Blank selection is showing in the IFC history. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Sreelakshmi R. | 3.3.4.1 | 3 - Medium
1142 | Bug | ITT_ Filter issue in IFC history. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Aneesha Chandramohan | 3.3.4.1 | 3 - Medium
1191 | Bug | Dev server_ Performance issue in IFC project loading. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Aneesha Chandramohan | 3.3.2.4 | 3 - Medium
1204 | Bug | Dev Server_ Current Revision number is empty for some items. | Active |  |  | Business |  | Aneesha Chandramohan | Not fixed | Bajila Salim | 3.3.5.0 | 3 - Medium
1156 | Bug | ITT_Export excel file not showing complete data | Resolved |  |  | Business |  | Minu Mohan | Deferred | Yamuna M S | 3.3.5.0 | 2 - High
1260 | Bug | An error message appears on NCM data analytics screen | New |  |  | Business |  | Aparna Raveendran | New | Nijil M K | 3.3.4.23 | 3 - Medium
1261 | Bug | IEP logs out automatically when we switch individual to office mode | New |  |  | Business |  | Aparna Raveendran | New | Nijil M K | 3.3.4.23 | 3 - Medium
917 | Bug | Dev server_The normal user should not have the permission to access the tools only the previleged users have it. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Aneesha Chandramohan | 3.3.3.36 | 3 - Medium
1042 | Bug | Dev server: Unable to Select the Activity ID from the tabular data when mandatory column are hidden in tabular data (ISPO - Early_status, VDR&VDRRev- Status) | Active |  |  | Business |  | Aparna Raveendran | Not fixed | Thanseer P.R. | 3.3.4.0 | 3 - Medium
1044 | Bug | Dev Server: While exporting large data , the process getting failed | Resolved |  |  | Business |  | Aparna Raveendran | Deferred | Bajila Salim | 3.3.4.0 | 3 - Medium
1242 | Bug | Dev server_ Help info is missing in Bom comparison, global operations, yield. | New |  |  | Business |  | Aneesha Chandramohan | New | Amala M R | 3.3.5.0(Dev server) | 3 - Medium
1045 | Bug | Dev Server: Showing undefined for some Resource name | Resolved |  |  | Business |  | Aparna Raveendran | Deferred | Aparna Raveendran | 3.3.4.0 | 3 - Medium
1041 | Bug | Dev Server: Subhra change user details from ‘Change Dashboard ‘ . it is reflected in left side ‘My Contract’ But it is not reflected in ISPO summary and tabular view. | New |  |  | Business |  | Aparna Raveendran | New | Bajila Salim | 3.3.4.0 | 3 - Medium
395 | Bug | IEP- General - Certain API is calling continuously and data is not loading in all screens of IEP. | Resolved |  |  | Business |  | Reshmimol K.K. | Deferred | Thanseer P.R. | 3.3.3.26 | 2 - High
597 | Bug | Operation->ISPO->OTD Trends: Active office and old offices are not available seperately(Req id:IEPPHASE4REQ-92) | Resolved |  |  | Business |  | Aparna Raveendran | Deferred | Aparna Raveendran | 3.3.3.292 | 3 - Medium
773 | Bug | Dev_Server :- Due tab should be present in Action item notification | Resolved |  |  | Business |  | Shreedevi I. Manjari | Deferred | Shreedevi I. Manjari | 3.3.3.3 | 3 - Medium
898 | Bug | Dev server_ Two entries are showing while updating the version number. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Urvasi G. | 3.3.3.33 | 3 - Medium
899 | Bug | Dev server_ After the scheduler run sometime the tool management screen is not updating. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Urvasi G. | 3.3.3.33 | 3 - Medium
900 | Bug | Add/Enable column - Office combo box show the same structure of Office Filter. Contains a tree view with office and Division:Correct the UI with expand Collapse button | Resolved |  |  | Business |  | Aparna Raveendran | Deferred | Aparna Raveendran | 3.3.3.33 | 3 - Medium
901 | Bug | Dev server_ Excel tool should contain rev keyword followed by not other specified. | Resolved |  |  | Business |  | Aneesha Chandramohan | Deferred | Urvasi G. | 3.3.3.33 | 3 - Medium
902 | Bug | Show -Hide column - After closing required a loading icon for column refresh. Otherwise user not get an idea of update: The loading icon is not yet available | Resolved |  |  | Business |  | Aparna Raveendran | Deferred | Aparna Raveendran | 3.3.3.33 | 3 - Medium
905 | Bug | Dev_Server : In 60% Guideline images should not be visible clearly | Resolved |  |  | Business |  | Shreedevi I. Manjari | Deferred | Shreedevi I. Manjari | 3.3.3.33 | 3 - Medium
923 | Bug | Dev Server:PT - Header not visible when scrolling the page. | Resolved |  |  | Business |  | Aparna Raveendran | Deferred | Aparna Raveendran |  | 3 - Medium
928 | Bug | My Contract/All Contracts - Active Projects/Past projects Header is not showing while we scroll the Projects. Need to fix the Header | Resolved |  |  | Business |  | Aparna Raveendran | Deferred | Aparna Raveendran | 3.3.3.37 | 3 - Medium

## IEP-Bugs Set 2
ID | Title | State | Assigned To | Remaining Work | Created By | Created Date | Reason | Resolved Reason | Closed Date | Defect Type | Integration Build | Severity | Found In
11795 | Production Issue - IEP-Offline Issue - Observations. | Resolved | Reshmimol K.K. |  | Reshmimol K.K. | 2021-07-12 10:08 | Deferred | Deferred |  | Interface specification |  | 2 - High | 3.3.2.3
11699 | ITT_ EMST 60%_ Guideline picture is missing in the excel export and reviewer's checklist. | Resolved | Aneesha Chandramohan |  | Aneesha Chandramohan | 2021-08-11 15:18 | Deferred | Deferred |  | Functionality |  | 3 - Medium | 3.3.3.1
11737 | ITT_ EMST 60% _ Alignment issue. | Resolved | Aneesha Chandramohan |  | Aneesha Chandramohan | 2021-11-11 12:13 | Deferred | Deferred |  | Logic |  | 3 - Medium | 3.3.3.11
11755 | Dev server _ Performance issue in contracts loading. | New | Juby C. Samuel |  | Aneesha Chandramohan | 11/15/2021 6:56 PM | New |  |  | Functionality |  | 3 - Medium | 3.3.3.1
11756 | Dev Server & ITT Server 30% & 90% Guildeline Picture column not present in excel export file | Resolved | Shreedevi I. Manjari |  | Shreedevi I. Manjari | 11/15/2021 7:40 PM | Deferred | Deferred |  | Documentation |  | 3 - Medium | 3.3.3.1
11744 | Quality book - Dev server - No data displayed in generated PPT | New | Jeetu James |  | Jeetu James | 2021-12-11 13:41 | Not fixed |  |  | Functionality |  | 2 - High | 3.3.3.12

## IEP-Bugs Set 3
ID | Title | State | Assigned To | Remaining Work | Created By | Created Date | Reason | Resolved Reason | Closed Date | Defect Type | Integration Build | Severity | Found In
11530 | "Bugs like showing and not showing current resources/wrong resources are observed. To validate more on this. Sync Issue . Switching between Auto Assigned /Wrong resource and -Second API call get First API result" | Resolved | Mohamed Ilyaz Sulaiman |  | Teena Varghese | 2021-08-10 21:00 | Fixed | Fixed |  |  |  | 3 - Medium
11535 | For Some documents, DOC type is not avaialble in Tabular data. | Resolved | Mohamed Ilyaz Sulaiman |  | Teena Varghese | 2021-08-10 21:07 | Fixed | Fixed |  |  |  | 3 - Medium
11542 | TPO- Actual not correct | Active | Bajila Salim |  | Teena Varghese | 2021-08-10 23:15 | Not fixed |  |  |  |  | 3 - Medium
11544 | "When project status is selected as “Inactive”….why inactive projects are also in Current projects? If any open points in Inactive projects like VDR-REV , VDR-FIN or TA, can IEP highlight that sub module for attention(New used case)? " | Resolved | Mohamed Ilyaz Sulaiman |  | Teena Varghese | 2021-08-10 23:16 | Fixed | Fixed |  |  |  | 3 - Medium
11581 | P6 Resource- "Bugs like showing and not showing current resources/wrong resources are observed. To validate more on this. Sync Issue . Switching between Auto Assigned /Wrong resource and -Second API call get First API result" | Resolved | Mohamed Ilyaz Sulaiman |  | Teena Varghese | 2021-09-10 14:08 | Fixed | Fixed |  |  |  | 3 - Medium
11582 | Devserver _ SYSTEM DR1 _ PERFORMANCE ISSUE | New | Thanseer P.R. |  | Aswin Sreesh | 2021-09-10 21:41 | New |  |  | Functionality |  | 1 - Critical | 3.3.2.6
11585 | DEV SERVER_ SYSTEM DR1 _ Alignment of evidence pic in exported excel file. | Resolved | Aswin Sreesh |  | Aswin Sreesh | 2021-09-10 21:52 | Deferred | Deferred |  | Functionality |  | 3 - Medium | 3.3.2.6
11587 | Dev server _ System DR1 _ The picture for thumbnail files other than image files. | Resolved | Aswin Sreesh |  | Aswin Sreesh | 2021-09-10 22:07 | Deferred | Deferred |  | Functionality |  | 3 - Medium | 3.3.2.6
11626 | DEV SERVER _ BDR/DDR _ ISSUES WITH AREA FIELD | Resolved | Aswin Sreesh |  | Aswin Sreesh | 10/16/2021 3:10 PM | Deferred | Deferred |  | Functionality |  | 3 - Medium | 3.3.2.7
11637 | Dev server _ System DR1_ Pre work completed button navigates to wrong discipline value with invalid id no. | Resolved | Aswin Sreesh |  | Aswin Sreesh | 10/20/2021 11:48 AM | Deferred | Deferred |  |  |  | 3 - Medium
11598 | Dev server - ISPO- Late finish- Count mismatch in tabular data, chart, OTD trend | Active | Anu James |  | Reshmimol K.K. | 10/14/2021 3:10 PM | Not fixed |  |  | Functionality |  | 2 - High | 3.3.2.7 (dev server)
11620 | Dev server - Observation - VDR- the data is not correct in the exported file | Resolved | Reshmimol K.K. |  | Reshmimol K.K. | 10/15/2021 9:18 PM | Deferred | Deferred |  | Logic |  | 3 - Medium | 3.3.2.7
11635 | Devserver - ISPO/VDR - OTR trend - Columns are not displaying based on selection in tabular data (especially Issue number and Revision number) | Resolved | Reshmimol K.K. |  | Reshmimol K.K. | 10/19/2021 5:18 PM | Deferred | Deferred |  | Functionality |  | 3 - Medium | 3.3.2.7
11622 | Extra blank sheets are displaying in tabular data export file | Resolved | Jeetu James |  | Jeetu James | 10/15/2021 10:59 PM | Deferred | Deferred |  | Functionality |  | 3 - Medium | 3.3.2.7
11674 | Production server - favorites spelling not correct | New | Thanseer P.R. |  | Reshmimol K.K. | 10/27/2021 5:25 PM | New |  |  |  |  | 3 - Medium | 3.3.3.0
11675 | Production Server - Even the checkbox is in unselected state, the data is displaying. | New | Thanseer P.R. |  | Reshmimol K.K. | 10/27/2021 5:30 PM | New |  |  | Logic |  | 3 - Medium | 3.3.3.0
11676 | Production server - Column Name to be corrected | New | Thanseer P.R. |  | Reshmimol K.K. | 10/27/2021 5:31 PM | New |  |  | Logic |  | 3 - Medium | 3.3.3.0
11417 | PE-FPE HandOver - There is no option to identify the newly assigned FPE. | Resolved | Reshmimol K.K. |  | Reshmimol K.K. | 9/28/2021 3:53 PM | Deferred | Deferred |  | Functionality |  | 3 - Medium | 3.3.2.51
11466 | ITT_ RR EMST_ Mismatch in the column name and item is missing in the action item notification. | Resolved | Aneesha Chandramohan |  | Aneesha Chandramohan | 2021-02-10 19:20 | Deferred | Deferred |  | Resource/ Data handling |  | 3 - Medium | 3.3.2.51
11304 | Legends overlapping in VDR finalization trend chart | Resolved | Jeetu James |  | Jeetu James | 8/31/2021 2:59 PM | Deferred | Deferred |  | Standards |  | 3 - Medium | 3.3.2.43
11398 | IEP-Sanity test- UI issues | Resolved | Reshmimol K.K. |  | Reshmimol K.K. | 9/16/2021 7:27 PM | Deferred | Deferred |  | Logic |  | 3 - Medium | 3.3.2.46
11401 | IEP- Sanity test - Select all button not working for past projects | Resolved | Jeetu James |  | Jeetu James | 9/17/2021 12:47 PM | Copied to Backlog | Copied to Backlog |  | Functionality |  | 3 - Medium | 3.3.2.5 dev
11407 | Eng runrate - There is a slight data mismatch for platform , product and projects. | Resolved | Reshmimol K.K. |  | Reshmimol K.K. | 9/27/2021 11:05 AM | Deferred | Deferred |  | Functionality |  | 3 - Medium | 3.3.2.5
11648 | As Built Tabular data icon issue - Export is blue and remaining is black | Resolved | Gireesh Areekkal |  | Gireesh Areekkal | 10/22/2021 2:30 PM | Deferred | Deferred |  |  |  | 3 - Medium